## template
Project Name	Botnet
File Name	server.c
Function Name	bot_command
Tester's Name	Cody
Date of Testing	23/04/2020

Test ID	Test Case	Test Steps	Test Data	Expected Result	Actual Result	Pass / Fail	Fixed?
Example_001	Display help screen	Input "help"	help	Help screen displayed in terminal	Help screen was displayed	Pass	N/A

## Connectivity
Project Name	Botnet
File Name	server.c / client.c / simple_networking.h
Function Name	Connectivity
Tester's Name	Zak
Date of Testing	16/05/2020

Test ID	Test Case	Test Steps	Test Data	Expected Result	Actual Result	Pass / Fail	Fixed?
Connection_01	Connect single client to the server locally	Run the client program on the same network with the server		client connects successfully	Client was connected	Pass	N/A
Connection_02	Connect a client globally	The client machine is on a different LAN than the server		client connects successfully	Not tested
Connection_03	Connect to multiple clients	Execute the client program on multiple machines on the same time		multiple connection achieved	clients connected successfully	Pass	N/A
Connection_04	Connect when server is down	Run the clinet program while server is not running		Wait for the sever to connect?	Unable to connect
Conncetion_05	Connect to wrong server IP address	input wrong server IP address in the file client.c and execute		connection refused	Connection refused	Pass	N/A
Conncetion_06	Server ends connection with the client remotly	input exet on the server terminal		Connection is terminated	Connection was terminated	Pass	N/A
Conncetion_07	Client machine terminates the connection	kill the process from the terminal on the client machine using "ctrl c"		termination refused	termination refused but after receiving the next command from the server, the connection ends.	Pass?

## Input
Project Name	Botnet
File Name	server.c
Function Name	bot_command
Tester's Name	Cody
Date of Testing	14/04/2020

Test ID	Test Case	Test Steps	Test Data	Expected Result	Actual Result	Pass / Fail	Fixed?
bot_command_001	Bad input on console page	Input "cd .."	cd ..	Re-prompt	As expected	Pass	N/A
bot_command_002	Bad input on console page	Input "ls"	ls	Re-prompt	As expected	Pass	N/A
bot_command_003	Bad input on console page	Input "~/"	~/	Re-prompt	As expected	Pass	N/A
bot_command_004	Bad input on console page	Input "HELP"	HELP	Re-prompt	As expected	Pass	N/A
bot_command_005	Bad input on command page	Input "cd .."	cd ..	Re-prompt	As expected	Pass	N/A
bot_command_006	Bad input on command page	Input "Single"	Single	Re-prompt	As expected	Pass	N/A
bot_command_007	Bad input on command page	Input "cd .."	cd ..	Re-prompt	As expected	Pass	N/A
bot_command_008	Bad input on command page	Input "~/"	~/	Re-prompt	As expected	Pass	N/A
bot_command_009	Bad input on command single page – connect to 5th client when only 1 client connected	Input "5"	5	Print error w/ correct number of clients. Exit to command screen	As expected	Pass	N/A
bot_command_010	Bad input on command single page	Input "one"	one	Print error w/ correct number of clients. Exit to command screen	Connected to client [0] (server). When command was sent. Server exited and so too did client.	Fail
bot_command_011	Display help screen on command single page	Input "help"	help	Print help screen with list of commands to send to client	Server hung and was unable to interact further. Client executed help command.	Fail
bot_command_012	Bad input on command single client	Input bad command	badcommand	Client would return badcommand: not found	Client returned: [hostname] e.g. (Cody’s PC)	Fail
bot_command_013	Bad input on command single client	Input “merr”	merr	Client would return merr: not found	Server hung with no return data from client and was unable to interact further. Client executed merr command and output “merr: not found”	Fail
bot_command_014	Good input on command single client	Input “ls”	ls	Connected client return list of files in current directory	As expected	Pass	N/A
bot_command_015	Good input on command single client	Input “cd ..”	cd ..	Client would change directory, server re-prompt for next command	Segmentation fault on server. Client spammed “Server said: ” and “Completed Command: “	Fail
bot_command_016	Good input on command single client – check for known installed program	Input “which firefox”	which firefox	Client will return location of firefox	As expected	Pass	N/A
bot_command_017	Good input on command single client – check for known not installed program	Input “which lynx”	which lynx	Client will not return and server will re-prompt for next command	Server hung with no return data from client and was unable to interact further. Client received command from server and executed.	Fail
bot_command_018	Good input on command single client – execute known program	Input “firefox”	firefox	Client will execute firefox and browser will open	As expected	Pass	N/A
bot_command_019	Display help screen on command all clients	Input “help”	help	Print help screen with list of commands to send to all clients	Server hung with no return data from client and was unable to interact further. Client received command from server and executed.	Fail
bot_command_020	Good input on command all clients	Input “ls”	ls	Connected clients return list of files in current directory	Client 1 returned list of items in current directory and then Server got segmentation fault. Client shows executed ls command. Also shows server sent 3 additional empty commands which were executed by client - “Server said: “ “Completed command: “ x3	Fail
bot_command_021	Good input on command all clients	Input “cd ..”	cd ..	Client would change directory, server re-prompt for next command	Segmentation fault on server. Client spammed “Server said: ” and “Completed Command: “	Fail
bot_command_022	Good input on command all clients – check for known installed program	Input “which firefox”	which firefox	Clients will return location of firefox	Client 1 returned list of items in current directory and then Server got segmentation fault. Client shows executed ls command. Also shows server sent 3 additional empty commands which were executed by client - “Server said: “ “Completed command: “ x3	Fail
bot_command_023	Good input on command all clients – check for known not installed program	Input “which lynx”	which lynx	Clients will not return and server will re-prompt for next command	Client 1 returned host name and then Server got segmentation fault. Client spammed “Server said: ” and “Completed Command: “	Fail
bot_command_024	Good input on command all clients – execute known program	Input “firefox”	firefox	Clients will execute firefox and browser will open	Client 1 executed firefox and browser opened, then server got segmentation fault.	Fail

## Persistence
Project Name	Botnet
File Name	client.c
Function Name	Persistence
Tester's Name	Will
Date of Testing	16/05/2020

Test ID	Test Case	Test Steps	Test Data	Expected Result	Actual Result	Pass / Fail	Fixed?
Persistence_001	Excutable copy	Input remote"exit" command on the server side	client	client disconnect with a executable copy created	copy was successfully create at the home directory	Pass	N/A
Persistence_002	Executable copy	delete the home dir client copy while connection is up	client	Unknown (experimenting)	new client copy was not created	Fail?	N/A
Persistence_003	Executable copy	making the client connection while a dir named client is present in the home dir	client	Unknown (experimenting)	client copy cannot overwrite	N/A	N/A
Persistence_004	Executable copy	run client using the executable	client	connection to server to be made	connection was successful	Pass	N/A
Persistence_005	Executable copy	connecting client while a txt file named client exists	client	client executable copy can be created	copy was successfully create at the home directory	Pass	N/A
Persistence_006	Executable copy	changing the client copy's name	client	client can no longer be executed using the old name	file not found in the directory	Pass	N/A
Persistence_007	Executalbe copy	ctrl C on the client machine to simualte machine shut down	client	server command able to go through to the client	csigint recv shown, command received from server but connection is terminated	Fail?	N/A